# GOES-N: Long and Winding Road to Launch

Operating as a two-satellite constellation 22,000 miles above Earth’s equator, the GOES (Geostationary Operational Environmental Satellite) observatories provided continuous meteorological coverage of 60 percent of the planet. GOES-N, the first in the next generation of GOES spacecraft, would be the most advanced meteorological observation satellite in space.

Getting GOES-N into orbit, however, would prove to be difficult. The road to launch was marred by a series of unfortunate events, including lightning strikes in the vicinity of the rocket, launch-vehicle battery qualification issues, and contractor technician strikes. For months GOES-N sat on the ground, stacked and waiting, riding out a sequence of delays and resets as engineers and managers wrestled with a string of issues.

By the summer of 2005, Ken Yienger, systems manager for GOES-N, couldn’t help but wonder, What next? “As a systems engineer,” Yienger said, “you are always focused on making sure you have done everything possible to assure a successful mission right up to the moment of launch—testing, retesting, verifying, and validating everything multiple times. Then you close the launch vehicle fairing and say, ‘Let’s go!’ You expect some unexpected things—bad weather that will delay you a day or so on the pad, or a shuttle mission might make you wait a few days. But nobody plans upfront to sit on the launch pad for a month.”

With the GOES-N team facing a host of technical and programmatic issues and project members rescheduling commitments…with the original launch date of December 2004 receding in the rear-view mirror and the 2005 hurricane season approaching…the central question was: When have an observatory and launch vehicle sat too long on the pad?

# Best in the Sky

Developed by NASA for the National Oceanic and Atmospheric Administration (NOAA), GOES was critical to the forecasting and tracking of severe weather such as hurricanes and tornadoes. Remaining in one position relative to the rotating Earth, the GOES satellites were relied on by the global meteorological community to send a continuous stream of weather and environmental data. GOES was known as the world’s “eyes in the sky”—the only weather forecasting tool for many of the 140 nations that received the satellites’ data. The observatories were also the linchpin to the SARSAT (search-and-rescue satellite-aided tracking) system that relayed emergency signals sent from aircraft, marine vessels, and emergency locator transmitters. Over the past 25 years, SARSAT, assisted by GOES, had initiated the rescue of more than 18,000 people.

# GOES N: Leading the Next Generation

A three-axis stabilized spacecraft built on the Boeing 601 heritage design, the GOES N series of satellites (including GOES-O and -P) was designed for a nominal 10-year mission life (with 14 years of fuel) per satellite. The “stellar inertial-based” attitude control system comprised three star trackers and a hemispherical inertial reference unit for determination/control; four reaction wheels to control the spacecraft in the normal mode; and 12 two-pound thrusters to manage momentum and maintain orbital location.

GOES-N (to be designated GOES-13 once in geosynchronous orbit) carried a collection of Earth- and space-monitoring instruments that advanced previous technology, and was built with more accurate prediction and tracking capabilities than any of its 12 predecessors. It was designed to improve, by a factor of four, image accuracy in locating severe weather events, largely by virtue of its star-tracker navigation system.

The primary instrument suite of GOES-N consisted of:

- 5-channel imager: a radiometer for producing images of the Earth’s surface, oceans, storm development, cloud cover, cloud temperature and height, surface temperature, and water vapor; developed by ITT.

- 19-channel sounder: a supplementary device to the imager for gathering data for determining atmospheric temperature and moisture profiles, surface and cloud-top temperatures, and ozone distributions; also built by ITT.

- Solar x-ray imager for providing early detection and location of solar flares and for gauging flare intensity and duration; developed by Lockheed Martin.

- Space environment monitor instruments provided by Boeing, including a 3-axis magnetometer for measuring energy particles and Earth’s geomagnetic field, built by SAIC, and a particle and solar monitoring suite from ATC/Panametrics.

GOES-N boasted other enhancements as well: a digital transmission system for dissemination of data products that were distributed in analog format in the previous generation of GOES satellites; an enhanced power subsystem using a single-panel solar array; and a satellite design lifetime enhancement from 7 to 10 years, and expected propellant lifetime increase to 13.5 years.

Figure 2. GOES coverage: Continuous observation of 60 percent of the Earth, including the entire continental United States.

# The Project Team

Three main players made up the GOES-N project team: Boeing Satellite Systems, Inc. (BSS), Goddard Space Flight Center (GSFC), and National Oceanic and Atmospheric Administration (NOAA). BSS was building the satellite and Boeing Expendable Launch Services (BELS) was providing the launch vehicle (LV), a Delta IV (4+2) rocket, as well as launch services. GSFC was procuring the observatory components, including the observatory and instruments. The Center was also responsible for overseeing the development, testing, and operations of the spacecraft, instruments, and ground equipment during the post-launch check-out phase. NOAA was responsible for the overall program, funding, system on-orbit operation, and processing and dissemination of environmental satellite data for the United States. It also had operational responsibility for the ground system.

Launch services were to be provided by BELS through a fixed-price “delivery on-orbit” contract between NASA and BSS. Costs of any delays during the launch campaign—both observatory and LV costs—would be borne by the contractor. Under terms of the contract, there would be cost penalties for schedule-related delays that were specifically exercised by NASA—in other words, “NASA delays, NASA pays.”

NASA and NOAA went into the GOES-N series acquisition with the mindset of a modified-commercial, “delivery-on-orbit” approach utilizing a firm fixed-price contract for both the observatory development and launch services. While highly leveraging Boeing’s experience in commercial satellite development and operations, NASA focused its expertise and involvement on delivering the GFE instruments and on lowering and mitigating mission risks—working whenever possible within the scope and terms of the existing contract. As a result, although technically frustrating to the NASA team, who wanted its own processes and styles to be followed, the arrangement meant, programmatically, that the risks and costs for schedule delays were being burdened by the prime contractors rather than NASA/NOAA. Nonetheless, any unilateral direction given (or implied) by NASA would place (larger) financial burdens on the agencies for the costs of both the observatory and launch-vehicle contractors.

Boeing was allowing 24 days after launching GOES-N for the spacecraft to reach geosynchronous orbit at 22,240 miles, at which time the satellite’s instruments would be deployed and powered up. GOES-N would then be renamed GOES-13 and turned over to NASA for post-launch engineering checkout.

Eventually, GOES-13 would be handed off to NOAA and placed in on-orbit storage mode, waiting to be activated when either GOES-11 (West) or GOES-12 (East) suffered an anomaly or exhausted its fuel. Once called into service, GOES-13 would deploy its instruments and begin its vigil of observing and measuring meteorological and environmental phenomena on Earth and in space.

# Roadblocks…

But getting GOES-N to launch was taking years. Observatory developmental issues accounted for little of the delay time. Rather, several delays and resets had occurred due to launch-vehicle–related technical issues after the spacecraft had completed observatory environmental testing.

About midway through the development of the spacecraft, the decision was made to manifest GOES-N-P on the new Boeing Delta IV launch vehicle. While the decision had little effect on the spacecraft’s design and testing, GOES-N was one of the first of the Boeing Delta IVs, and as with all new launch vehicles, development issues were causing the LV queue to slow down while early flight issues were addressed. In addition, because GOES-N was the first launch of this series of spacecraft, NASA was more cautious with the launch windows, choosing not to allow the observatory to be launched during the spring and autumnal eclipse periods. These forces were contributing to a slower-than-normal road to space.

By March 11, 2005, the spacecraft had arrived at the launch site and a number of tests had been completed, including spacecraft functional testing, instrument testing and cleaning, and blanket closeout. An issue in a solar sensor had been repaired, and other activities had taken place around this time as well: Observatory battery performance testing (capacity check) was completed, and on April 7 the spacecraft was fueled. On May 25, 2005, the spacecraft was mated to the payload attach fitting (PAF). It was encapsulated on June 3, and five days later it was transported to Cape Canaveral in preparation for the initial June 23, 2005, launch date.

Then a combination of problems converged to delay the launch attempt until August 15: new technical issues related to the spacecraft’s communication boxes, a “close-in” lightning strike from a summer thunderstorm that required evaluation and testing, and ongoing issues with the launch vehicle’s composite over-wrapped pressure vessel (COPV) tanks. For a spacecraft team, few things are more agonizing than sitting on the launch pad.

Ken Yienger, the systems engineer, recalled the frustration:

We had done everything we felt was necessary to launch and had made some compromises to get where we were. We sat there, buttoned down in the fairing waiting for the next attempt, unable to fully and ideally test the observatory as we’d like.

Meanwhile, additional “what-if’s” and collateral hardware issues back at the factory continued to come across the radar screen. We alternated between being blessed with the GOES-O and GOES-P observatories still being tested in the high-bay—we could troubleshoot anomalies on sister spacecraft—to cursed, since now all issues were “launch liens,” and needing to figure out, “How are we going to test THAT in a launch vehicle fairing?” Each issue, individually, was one we felt we could chase to ground, but, like snowflakes, each one can aggregate into a much bigger issue. At the end of the day we had to keep asking: Are we still ready to launch?”

# Pre-Launch Reflections

It is August 14, 2005. You are the GOES-N mission systems engineer or observatory manager. You have successfully retired all pre-launch actions. Earlier in the day the Launch Readiness Review (LRR) had gone well, and you have received concurrence from NASA HQ and GSFC management to proceed with launch.

You review some of the key observatory milestones over the past year:

- Environmental (SCTV) testing and battery activation and acceptance testing were completed in August 2004.

- Ambient performance testing (comprehensive) was done in December 2004.

- Battery performance had been verified (limited capacity check) on March 25.

- Spacecraft had been fueled and flight-pressurized on April 7.

- Spacecraft was encapsulated on June 8.

- Batteries had been charged to flight SOC (70% SOC) on July 18.

You think back on some of the distinguishing characteristics of the mission:

GOES was a NASA Class B mission: high value/high visibility. The replacement cost for the GOES-N observatory was estimated at $500 million to $750 million. Launch delays were costly—commercial launch service meant “you stop, you pay,” and NASA-directed stand-downs incurred a penalty of $250,000/day (no penalty for any other stand-down).

The “ship and shoot” nature of the launch service meant that testing capabilities at the launch site were limited by MGSE/EGSE (mechanical/electrical ground support systems) availability. Also, there were typical testing restrictions on the pad due to location and payload fairing (e.g., limited to umbilical-provided services only, hardline communications). Destacking required a minimum of 25 days for five days of “vehicle free” testing.

Finally, you think about the challenges that had caused delays. Technical hurdles had exposed some personnel and management issues, specifically the extent to which technical personnel should play a role in assessing launch risk, and in the go/no-go decision itself.

Foremost in your mind is one question: What constitutes a reasonable on-ground duration without retesting—how long is too long to sit?

# Decision Time

Four days later, GOES N is still on the ground. Two launch attempts—August 15 and 16—were unsuccessful, the first due to a COPV pressure drop in the launch vehicle, the second because of a battery problem in the LV. On the second attempt you were only 4 minutes, 20 seconds from launch.

On August 18, to further complicate your life, the LV’s flight termination system (FTS) batteries expired and new ones would not be available for a minimum of three weeks—pushing you into the autumn eclipse season. Based on all this information, your new launch date appears to be November 2.

The observatory has now been on the pad for five months, encapsulated for more than two months. Some of the tests had been done as long as a year ago. That nagging concern about on-ground duration keeps coming back. Time to decide:

- What will you recommend to the project manager:

  - Sit and wait?

  - Restack?  Retest?

  - Let the contractor make the call?

- What types of analyses will you recommend?

- What additional on-pad testing should be done?

- What criteria do you factor into the decisions?

# GOES-N Launch Timeline

| Date | Event |
| --- | --- |
| January 1998 | Contract signed to procure next-generation weather satellites. |
| 2001 | Originally scheduled for launch in 2001; construction/launch extended to 2003 because the GOES satellites already on-orbit are working well. |
| 2003 | Scheduled for launch in December 2004, then January 2005. |
| Early 2005 | Launch date reset to May 2005 to avoid launching during spring eclipse season. |
| May 27, 2005 | Mission Readiness Review (MRR) |
| April 2005 | Concern about Delta IV rocket delays postpones to June; tanks replaced. |
| June 2005 | June 7: Safety, Mission Assurance Readiness Review (SMARR) June 13: NASA HQ Mission Readiness Briefing (MRB) Mid-June: Launch slips to late June to allow time to check for possible damage to rocket’s electrical systems from lightning strikes. Late June: Uncertainty about a rocket battery postpones launch to July. |
| July 2005 | Technical concerns about launch vehicle and satellite delay to August. July 22: Flight Readiness Review (FRR) |
| August 2005 | August 14: Launch Readiness Review (LRR) August 16: Launch aborted with 4 minutes, 22 seconds to go. Because launch slips past mid-August, it is rescheduled for the first weekend in November 2005 to avoid risk of deployment during autumnal eclipse season in geosynchronous orbit. |
| October 2005 | Spring eclipse season makes launch risky; rescheduled for after mid-April. Boeing takes satellite off rocket, rehabs both, puts them back together. |
| Nov. 2005 | Boeing union votes to strike, launch is put on hold. |
| April 2006 | NASA MRR, SMSR and MRB successfully held, clearing GOES-N for May launch. |
| May 24, 2006 | GOES-N launched on Delta IV to nearly direct injection to geo-orbit. After launch, Boeing schedules 24 days to get to geosynchronous orbit, deploy, and outgas all components, power-up (but not open up) instruments, and rename satellite GOES-13. |
| June 13, 2006 | After 20 days of preparation, Boeing turns GOES-13 over to NASA for post-launch engineering checkout of approximately 240 days. |
| June 22, 2006 | First visible image taken, five days ahead of schedule. |

Source: Adapted from “GOES-N Launch Saga Timeline,” http://goes.gsfc.nasa.gov/text/goesnstatus.html

# Text boxes

Figure 1.  Artist’s depiction  of GOES overlooking Earth.

Figure 3. The Delta IV rocket for GOES-N, 
Launch Complex 37 at Cape Canaveral Air 
Force Station.

Figure 4. Still standing ready to launch at Cape Canaveral.