NASA Case Study

Launching the Vasa

Laid down in 1626, a lot rode on the men who were building the Swedish gunship Vasa and those who would sail her. It had been a calamitous decade for the Swedish Navy, during which 12 of Sweden’s largest warships had been captured, wrecked, or scuttled. A violent storm in 1625 destroyed 10 of those, prompting the imperious King Gustav II Adolf to order four new ships. Further losses dramatically increased the King’s impatience with his shipbuilders.

Make it Longer!

First ordered as a small, traditional ship, after numerous change orders from the King it was increased in both size and armament. A 111-foot keel was laid down, but almost immediately work stopped as the King learned that rival Denmark was building a larger ship with two gun decks, a new innovation. The Vasa’s keel was ordered to be increased to 135 feet and the ship was now to include two enclosed gun decks.

No one in Sweden had ever built such a ship, and with the King making constant and ever-louder demands for both larger dimensions and faster delivery, there was no time for plans to be engineered. It was decided that scaling up the 111-foot keel, rather than laying a 135-foot keel, would save time.

This case was developed by the Goddard Knowledge Management Office with support from the NASA Academy of Program/Project & Engineering Leadership (APPEL. http://www.appel.nasa.gov) for the purpose of discussion and training. The material here is extracted from publicly available sources. It is not a comprehensive account of the mission and should not be quoted as primary source. Feedback on this case document may be sent to Edward.W.Rogers@nasa.gov or (301) 286-4467.

The shipbuilders added a fourth scarf to lengthen the keel but the result was narrow in relation to its length and the draft very shallow for a ship of that size. A foot and a half was added to the beam but because the keel was already laid it had to be added to the uppermost parts of the ship. This raised the center of gravity and contributed to the ship’s instability. The shallow keel did not allow sufficient room for the ballast needed to stabilize a ship of this size, and the narrow beam required extra bracing timbers, further reducing room for ballast.

More Guns !

A bigger ship needs more and bigger guns, demanded King Gustav. After many more revisions, he insisted upon 64 24-pounders, half on each deck, plus numerous smaller guns. The upper deck now had to carry the added weight of 24-pounders though it was built for 12-pounders, further raising the center of gravity. In the end, the rushed schedule allowed for only 48 24-pounders.

Adding to the top-heavy condition were hundreds of ornate, gilded, and painted carvings made of heavy oak, also ordered by the King. Meant to outshine the Danish ship, no cost was spared, and the Vasa became the most expensive ship of its time.

Management Change

In 1626 the head shipbuilder became very ill and while bed-ridden had to share his duties with two others, confusing project management. Division of responsibility and communication was weak, exacerbated by the King’s impatience and ever-changing demands, resulting in further delays. With the largest workforce in Sweden’s history essentially running amok, the shipbuilder finally died in 1627.

At the time, there were no standardized calculations for center of gravity, heeling characteristics, and stability factors. Ship captains learned their ships’ characteristics by trial-and-error testing. Even contemporary naval experts believed that the higher and more impressive a ship, and the more guns it carried, the more indestructible the ship would be.

Launch Readiness Test

Finally all that remained was a test of the Vasa’s seaworthiness. Called a “lurch” test, the ship’s captain and the King’s admiral had a skeleton crew of 30 men run from gunwale to gunwale amidships on a windless day in calm harbor waters. After three such sprints, the test was stopped because the ship was rocking so violently that the captain feared the ship would capsize. The shipbuilders were not present nor were they informed of the test results. No action was taken after the alarming results because the only known corrective course was ‘more ballast,’ which was not a viable option. Already loaded with 120 tons of ballast, there was no room for more. Even if there had been more room, the additional weight would have put the lower-deck gun portals near or below the waterline. As it stood, those ports were only 3 ½ feet above the waterline.

The Launch

It is July 25, 1628. You are the King’s admiral. You are under orders to launch today or suffer severe personal and professional consequences. You are being held responsible for the careers of the shipbuilder and shipwright, and the lives of the ship’s captain and his 150-man crew. You are also responsible for the  image of an expansionist Sweden and its main weapon, the Swedish Navy, now severely crippled by losses during wartime.

Reluctant but obedient and unwilling to stall any longer, on August 10, 1628, you order the ship to be pulled away from the wharf. A few sails are raised just as a light breeze picks up to fill the sails. The breeze fills the ships sails and lifts spirits. The Vasa sails about 1,000 yards, heels over, and sinks in view of the entire spectator crowd. Fifty souls are lost along with the entire ship. What went wrong? What would you do differently next time? Fortunately, you have access to some of the risk analyses (see below) done during the project to look for clues and lessons learned.

Crunch Time

King Gustav was in Poland campaigning and out of communication, though he had ordered that the ship be launched by July 25 and “if not, those responsible would be subject to His Majesty’s disgrace.” Neither the shipwright nor the shipbuilder had been present for the lurch test, and no one had suggested any ideas for increasing the Vasa’s stability. You know that upon the King’s return there will be a royal board of inquiry and you will have some tough questions to answer. You start thinking about them now to prepare yourself for what lies ahead. You decide to call together a small group of your trusted advisors and together you mull over these questions:

- Who is responsible for this catastrophe?

- Were there any inappropriate risks that should not have been taken? How can these be identified and mitigated on future shipbuilding initiatives?

- How can unknown areas be addressed beyond relying on the shipbuilder’s personal expertise? How do we advance into areas that are unknown?

- How could the communications between the King, the shipbuilders, and the Navy command be improved for the contracting, building, and delivery of future warships in a timely, on-schedule, and within-budget manner?

- What is the most important thing we can do to prevent this type of disaster from happening again?

Sources

Cederlund, Carl Olof and Hocker, Frederick M., ed., Vasa I: The Archaeology of a Swedish Royal Ship  of 1628, Statens Maritima Museer (January, 2007).

Fairley, Richard E. and Willshire, Mary Jane, “Why the Vasa Sank: 10 Problems and Some Antidotes for Software Projects,” IEE Software March/April 2003, IEE Computer Society.

Hendrickson, Elizabeth, “Going Down with the Ship, http://www.stickyminds.com (March 18, 2002).

Kvarning, Lars-Ake and Ohrelius, Bengt, The Vasa: The Royal Ship, Atlantic Bookforlag AB, 1998.

Mallin, Dea A., “Before the Titanic, There Was the Vasa,” http://theculturedtraveler.com/Archives/APR2005/Print/Vasa.htm

Mayol, Dottie E., “The Swedish Ship Vasa’s Revival,” http://www.abc.se/-m10354/pubbl/vasa.htm

“The Royal Ship Vasa,” http://hem.bredband.net/johava/WASA2e.htm

“The Vasa Capsizes: Managing Innovation,” http://dossantos.cbpa.louisville.edu/courses/cis675/vasa/index.htm

Selected VASA Project Risk Management Documents

| Risk Title: Complexity of Inter-Program Management Structure | Owner: Shipbuilder |
| --- | --- |
| Risk Statement: Given the complexity of the inter-program management structure in the Swedish Navy and the historic cultural differences between civilian, Naval and Royal offices; there is a possibility that integration of the VASA project will be negatively impacted. |
| Likelihood: 2 | Safety: 1 | Performance: 2 | Schedule: 2 | Cost: 2 |
| Context: There is a built-in complexity of the VASA organization and the work packages making system interfaces complex. This is most apparent between the shipbuilding team and the King’s Court. Requirements, design, and implementation processes, procedures and formal office to office agreements have not been documented. There are multiple approaches from different quarters in solving a common technical risk. The resulting impact to the VASA project is in not meeting schedule and inefficient implementation due to cultural differences and drivers witih foci that are different from that of the mission. |
| Status: Awaiting word from the King on design changes (July 1626) Death of Master Shipwright Hybertsson increases risk? (Spring 1627) |
| Mitigation Plan: The VASA project will watch this risk to see if it becomes an issue | Fallback Plan: Install more carvings of Norse Gods on the ship |

| Risk Title: Timely availability of skills / skills mix and cultural changes | Owner: Shipbuilder |
| --- | --- |
| Risk Statement: Given the current skill availability, mix and culture, there is a possibility that we may not be able to execute a new ship building project in a timely manner |
| Likelihood: 4 | Safety: 0 | Performance: 0 | Schedule: 4 | Cost: 0 |
| Context: The combination of the two different size ships being built simultaneously, the on-going war (affordability questions), the mix of older shipbuilders and new warfare strategies is pushing the project outside of known experience bases in size, weight, and operations designs. |
| Status: Interviewing key stakeholders for better understanding (July 1626) Schedule slips unavoidable due to changing requirements (Spring 1627) |
| Mitigation Plan: Research; interview the key stakeholders to identify skills gaps and cultural differences | Fallback Plan: Install more carvings of Norse Gods on the ship |

| Risk Title: Synchronization of Core Ship and the Gun Deck Architectures | Owner: Shipbuilder |
| --- | --- |
| Risk Statement: Given the existing challenges the VASA project is addressing and the instability in the VASA configuration; there is a possibility that the Gun Deck (war-fighting capability) project will not be able to maintain synchronized design analysis cycles leading up to an agreed architecture. |
| Likelihood: 3 | Safety: 0 | Performance: 3 | Schedule: 5 | Cost: 4 |
| Context: Both the ship core architecture (keel, beam, tonnage, and ballast) and the Gun Deck (armaments, configuration, gun mix and mass) have and continue to undergo revisions and requirements changes. This instability of requirements makes it difficult to synchronize the architectures and will likely require rework, and/or compromises that could impact the success of the mission. For example: The Armaments Command is requiring all 24-pounders (both gun decks) to standardize on gun fixtures and ammunition for efficient use in battle. |
| Status: Upper Gun Deck Ports already installed are too small for 24-pounders (Fall 1627). Schedule interchange meeting to compromise on upper deck guns. |
| Mitigation Plan: Attempt to synchronize the design and load cycles of both ship and weapons. | Fallback Plan: Install more carvings of Norse Gods on the ship |

| Risk Title: VASA vehicle test environment limitations | Owner: Shipbuilder |
| --- | --- |
| Risk Statement: Given the current VASA design concept (modified) has high stability test levels (load testing) and the adaptation of existing or modified structures (timbers) and components (guns, decorative art) is intended for use in many VASA applications; there is a possibility that the VASA project may incur schedule slips and increased cost due to subsystem failures requiring more system level test cycles to achieve qualification. |
| Likelihood: 4 | Safety: 1 | Performance: 3 | Schedule: 5 | Cost: 3 |
| Context: Historically some ship designs have failed (sunk due to instability) and required some redesign. Critical stability tests are driven by core ship design issues. Current schedule analysis indicates significant overlap between subsystem qualifications and completion of seaworthiness build, assembly and test cycles. |
| Status: VASA Project made highest priority by order of the King (Nov. 1625). Admiral Fleming to conduct a pre-launch “lurch” test with 30 seamen (July 1627) |
| Mitigation Plan: Results of “Lurch” test to be analyzed for adjusting ballast before launch. | Fallback Plan: Install more carvings of Norse Gods on the ship |

VASA SPECIFICATIONS

|  | Original Design Plan | After 1st Major Requirements Change | As Launched |
| --- | --- | --- | --- |
| Start Date: | January 1625 |  |  |
| Launch Date | 1626 | 1627 | August, 10, 1628 |
| Tonnage: | As for smaller ship | Added upper deck, guns and ship length | ca 1,200 t (2,650,000 lb) as estimated from excavation |
| Length: | 135 ft for the large ship 108 ft as a small ship 111 ft as laid down | 120 as called for by the King’s revisions | 135 ft as extended by a fourth scarf joint extension timber |
| Beam: | 34 ft for large ship Laid as specs for smaller ship (circa 20ft) | 24 ft as called for by the King’s revisions | 35 ft then up to 38.4 ft with (above water) widening timbers |
| Ballast: | Enough by builder’s judgment | Whatever will fit in the ballast area ! | 120 tons (as determined by excavation) |
| Draft: | As for small ship | As for large ship | 4.8 m (15.7 ft) after being weighed down with maximum ballast |
| Propulsion: |  |  | 10 Sails, total area of 1,275 m² |
| Crew: | Not known but less with the fewer armaments | 145 sailors plus 300 soldiers | 150 persons including women and children (probably relatives of the crew). No soldiers were on board. |
| Armament: | One Gun Deck with ports for 32 guns; 24 pounders - 32 | Two Gun Decks with up to 78 guns including: 24 pounders – 36 12 pounders – 24 48 mortars – 8 small guns - 10 | Two Gun Decks with 64 guns, including: 24-pounders - 48 3-pounders - 8 1-pounders - 2 Mortars - 6 |
| Cost: | Contract for 4 ships: two small and two large | No limit for the Kings honor was at stake | 200 Rex dollars 5% of Sweden’s GNP (billions and billions in today’s value) |

# Text boxes

A model showing the Vasa's hull profile, illustrating the shallow keel and two gun decks.